## Model Used
Scenario: You are assigned to develop a basic embedded system for an automotive industry application. The system will be a vehicle temperature monitoring system that reads the engine temperature using sensors and displays warnings on a small dashboard screen if the temperature exceeds a safe limit.
Model Used: Agile Development
Agile is suitable for your vehicle temperature monitoring system project because:
1. Iterative Development: Allows gradual integration and testing of components like sensors and dashboard display, ensuring early identification of issues. 2. Frequent Testing: Enables regular testing of sensor accuracy, data reading, and system responses to overheating, ensuring reliable performance. 3. Collaboration: Facilitates teamwork between hardware (sensors, microcontroller) and software (dashboard display, logic control) engineers for seamless integration. 4. Managing Uncertainty: Helps manage potential challenges with sensor calibration or display issues through flexible sprints. 5. Incremental Delivery: Delivers basic working versions early (e.g., initial temperature readings or warning alerts), allowing for continuous improvement. 6. Risk Management: Identifies risks such as sensor failure or display malfunctions early, preventing delays and ensuring system reliability. Agile’s iterative, flexible approach makes it ideal for handling the development of a real-time, sensor-based monitoring system in a dynamic automotive application.

## Planning
Project Plan
DevOps Phase | Tasks | Description
Project Planning | Requirement Gathering | Identify key features: sensor reading, warning display, safe temperature thresholds.
| Sprint Planning | Decide what to build in each sprint (sensor setup first, then warning system, then full integration).
| Resource Allocation | Assign roles to team members: embedded engineer, firmware developer, tester.
Project Design | Hardware Design | Select suitable temperature sensors, microcontroller, display (OLED/LCD).
| Firmware Architecture | Design modular firmware: sensor reading module, display module, warning module.
| Interface Definition | Define how modules interact (e.g., sensor to microcontroller via ADC, microcontroller to display via I2C/SPI).
Project Development | Sensor Integration | Write code to interface the temperature sensor and read values accurately to display it.
| Display the Sensor reading and Alert | Implement warning messages and buzzer alerts if temperature exceeds limits.
| Sprint Reviews | Regular reviews to show partial working models to the team for feedback
Validation and Testing | Unit Testing | Test individual modules (sensor read function, display output function, warning trigger function).
| Integration Testing | Test the entire flow from temperature reading to warning display.
| User Feedback Collection | Get feedback from testers or drivers on usability and clarity of alerts.
Deployment | System Installation | Mount the system inside a vehicle for real-world use.
| Release Documentation | Create user manual, installation guide, maintenance instructions.
Feedback and Launch | Feedback Collection | Gather feedback from initial users about system performance.
| Official Launch | Officially release and offer the system for regular use.

## Timeline
Sprint | Phase | Duration | Dependencies | Assignee
Spirint-1 | Project Planning | 1 week | Initial phase: Requirements study, user stories creation, sprint planning. | Project Manager and Stakeholders
Spirint-1 | Project Design | 1 week | After ID01: Hardware selection, firmware architecture, interface definition. | Emebedded System Engineer
Spirint-2 | Development Phase 1 | 2 weeks | After ID02: Sensor integration, basic display module, basic alert system. | Software Developer
Spirint-3 | Testing and Integration | 0.5 week | After ID03: Test individual modules like sensor read and display alert. | Embedded System Engineer and Quality Engineer
Spirint-3 | Development Phase 2 | 1 week | Based on feedback from ID04: Full system integration, optimization. | Embedded System Engineer and Software Developer
Spirint-3 | Validation (Field Testing) | 0.5 week | After ID05: Full hardware-in-the-loop and field tests. | Quality Engineer
Spirint-4 | Deployment | 1 week | After ID06: Install system in real vehicle setups. | Embedded System Engineer
Spirint-4 | Feedback & Project Closure | 1 week | After ID07: Collect real-time feedback, final optimizations, official launch. | Project Manager and Stakeholders
8 weeks

## Cost
Cost Estimate of the Project
Role | Responsibilities | Rate/hr (INR) | Hours/week | Weeks | Total Cost (INR)
Embedded Systems Engineer | Sensor interfacing, hardware design, firmware development | 80 | 30 | 9 | 21600
Software Developer | Display programming, warning logic, communication protocol (I2C/SPI) | 90 | 30 | 9 | 24300
Quality /Test Engineer | Unit testing, system integration testing, field testing | 50 | 20 | 7 | 7000
Hardware and software procurement | To realize and implement the temperature monitoring system |  |  |  | 50000
102900