## Choosing the Model
Scenario: You are assigned to develop a basic embedded system for an automotive industry application. The system will be a vehicle temperature monitoring system that reads the engine temperature using sensors and displays warnings on a small dashboard screen if the temperature exceeds a safe limit.
Choosen Model: DevOps
Why DevOps?
In embedded systems, hardware and software are developed in parallel. DevOps allows synchronized updates between firmware and testing environments (e.g., sensor drivers and diagnostic logic).
DevOps enables rapid iteration through CI/CD pipelines which can include simulation tools and hardware-in-the-loop (HIL) test stages. You can push updates to development boards or even OTA in connected vehicles with minimal manual intervention.
Automation Enhances Safety Compliance. Automated testing (unit, regression, integration) helps detect bugs earlier. Automotive standards like ISO 26262 benefit from repeatable, traceable test results—easily handled with DevOps pipelines.
Automated build, test, and deployment steps reduce the chances of manual mistakes. Automated dashboards help to detect the errors or faulty connections effectively which helps in timely maintenance for quality analysis.
DevOps enables scalable testing across variants. If the temperature system needs to work across different vehicle variants, DevOps can manage multiple build and test pipelines in parallel and this helps to reduce time-to-market across the vehicle lineup.
DevOps fosters cross-functional collaborative work. It encourages communication between developers, QA, system architects, and deployment teams. In automotive projects where system behavior must be verified at multiple levels, this collaborative model is invaluable.
DevOps supports Real-Time Monitoring & Feedback Loops. Logging and telemetry in test vehicles or benches can be easily deployed here. DevOps tools allow tracking field behavior and incorporating feedback into development cycles quickly.
DevOps efficiently handes edge cases. For instance, high-temperature readings in unusual scenarios (hill climbs, traffic jams). DevOps enables the team to reproduce and patch such issues quickly and confidently.
DevOps supports Modern Automotive Trends. As vehicles become more connected and software-defined (SDVs), DevOps becomes essential. Helps manage OTA firmware updates, diagnostics, predictive maintenance, etc.

## Planning
DevOps Phase | Tasks
Plan | Define system requirements: temperature limits, display alerts, safety standards.
Code/Develop | Write embedded source code for sensor data acquisition, threshold analysis, display control, integrate Git for version control.
Build | Set up cross-compilation pipelines for firmware; focuses on development and automation of the developed system.
Test | Write unit tests, simulation tests for sensor data and hardware-in-the-loop tests for quality control purpose.
Release | Tag and release stable firmware builds; prepare binaries for deployment.
Deploy | Flash to test boards or vehicle; use OTA update mechanisms, mainly focused on provisioning and configuration management.
Operate & Monitor | Monitor temperature readings in real-time using logs and containers and collect test data to visualize performance via dashboards.
Feedback & Improve | Conituous analysis of data, fixing bugs, enhancing logic; cycle back to Dev & Test phases.

## Timeline
Timeline ID | Phase | Duration | Dependencies | Assignee
ID01 | Planning | 1 week | This is the first phase where planning is properly done for the upcoming weeks based on thorough study of requirements. | Project Manager and Stakeholders
ID02 | Development Sprint 1 | 2 weeks | This phase is conducted from the 2nd week of the project after successful completion ID01. | Emebedded System Engineer
ID03 | CI/CD Setup + Build | 2 weeks | The pipelining process is conducted parallelly with ID02 for better analysis and continuous improvement stages. | Software Developer, Devops Engineer
ID04 | Unit + Simulated Testing | 1 week | After successful completion of ID02 and ID03, unit and simulated testing is conducted for one week to check the system environment and its functionalities in different types of real-time scenario. | Embedded System Engineer and Quality Engineer
ID05 | Development Sprint 2 | 2 weeks | Based on feedbacks from ID04 process, enhancements and bug fixing process are carried out . | Embedded System Engineer and Software Developer
ID06 | Hardware Testing | 1.5 weeks | After successful ID05, hardware testng is carried out. | Quality Engineer
ID07 | Deployment | 1 week | After ID06, deployment process is carried out in real time sytems. | Embedded System Engineer
ID08 | Monitoring & Feedback | 1.5 weeks | After ID07 (field testing/bench) | Project Manager and Stakeholders
10 weeks

## Cost
Role | Responsibilities | Rate/hr (INR) | Hours/week | Weeks | Total Cost (INR)
Embedded Systems Engineer | Sensor interfacing, hardware integration, firmware development. | 85 | 35 | 10 | 29750
Software Developer | Display logic, warning algorithms, DevOps automation (CI/CD). | 85 | 35 | 10 | 29750
QA/Test Engineer | Writing test cases, simulation & HIL testing. | 65 | 20 | 7 | 9100
DevOps Engineer | CI/CD pipeline setup, release management, OTA if applicable. | 90 | 20 | 7 | 12600
Project Manager | Planning, coordination, monitoring project progress. | 100 | 10 | 10 | 10000
91200