## Model Used
Scenario: You are assigned to develop a basic embedded system for an automotive industry application. The system will be a vehicle temperature monitoring system that reads the engine temperature using sensors and displays warnings on a small dashboard screen if the temperature exceeds a safe limit.
Model Used: V Model
Why V Model is suitable for your vehicle temperature monitoring system projec?
Well-Defined Requirements The system has clear functionality: read engine temperature, compare it with a safe threshold, and display warnings if exceeded. The V-Model is suitable for projects with stable and well-defined requirements, which align with the scenario. Emphasis on Testing at Every Stage Each development phase in the V-Model has a corresponding testing phase, ensuring errors are detected early. For example, unit tests can validate the sensor-reading functionality, while integration tests can ensure correct interaction between the sensor and dashboard. High Reliability and Safety Automotive systems must comply with strict safety standards (e.g., ISO 26262). The V-Model emphasizes verification and validation, ensuring the system is robust and reliable. Traceability of Requirements The V-Model provides excellent traceability, linking every requirement to corresponding tests and implementation phases. This helps verify that all safety and performance requirements are met. Hardware and Software Integration Embedded systems require tight integration between hardware (sensors) and software (dashboard interface). The V-Model ensures compatibility and seamless integration through its structured testing approach. Low Tolerance for Errors In embedded systems like this, errors in reading temperature or displaying warnings can lead to serious consequences. The V-Model's iterative testing approach minimizes the risk of late-stage defects. Alignment with Industry Practices The V-Model is commonly used in the automotive industry due to its structured approach and compatibility with automotive standards. It supports the development of systems requiring rigorous validation, like temperature monitoring.

## Planning
Project Plan
Phase | Tasks
Requirement Gathering | Identify functional and non-functional requirements. Define hardware and software needs. Ensure compliance with industry standards. Validate requirements with stakeholders.
System Design | Develop high-level architecture (hardware and software). Design sensor and dashboard integration. Create software design diagrams (flowcharts, data flow diagrams). Plan communication protocols and testing points.
Coding and Development | Write firmware for sensor data acquisition. Implement algorithms for data processing and alerts. Develop dashboard interface for temperature display. Perform code reviews for quality assurance.
Integration | Combine hardware and software components. Test hardware-software interaction. Ensure data flow and module communication.
Testing | Perform unit testing for individual modules. Conduct integration testing. Execute system testing for overall functionality. Validate system against requirements.
Deployment | Install the system in a test environment. Conduct field tests in real-world scenarios. Provide documentation (user manual, maintenance guidelines).
Post-Deployment Support | Monitor system performance. Address issues through updates or bug fixes. Log operational data for optimization. Provide firmware updates as needed.

## Timeline
Project Timeline
Timeline ID | Phase | Duration | Dependencies | Assignee
ID01 | Planning | 1 week | This is the first phase where requirements are gathered, and a plan is created. | Project Manager and Stakeholders
ID02 | System Design | 2 weeks | Conducted after ID01, includes architectural design and component selection. | Emebedded System Engineer
ID03 | Development Sprint 1 | 2 weeks | Starts after ID02 to implement sensor interfacing and dashboard logic. | Software Developer
ID04 | Unit Testing | 1 week | Conducted after ID03 to validate individual modules' functionality. | Embedded System Engineer and Quality Engineer
ID05 | Integration | 1 week | Conducted after ID04 to combine hardware and software components. | Embedded System Engineer and Software Developer
ID06 | System Testing | 1 week | Conducted after ID05 to validate the complete system's functionality. | Quality Engineer
ID07 | Deployment | 1 week | Conducted after ID06 to install the system in a test vehicle or setup. | Embedded System Engineer
ID08 | Monitoring & Feedback | 1 week | Conducted after ID07 for real-world performance testing and feedback collection. | Project Manager and Stakeholders
10 weeks

## Cost
Cost Estimate of the Project
Role | Rate/hr (INR) | Hours/week | Weeks | Total Cost (INR)
Project Manager | 100 | 10 | 10 | 10000
Embedded Systems Engineer | 90 | 30 | 10 | 27000
Software Developer | 80 | 20 | 10 | 16000
UI/UX Designer | 40 | 20 | 3 | 2400
Quality Assurance Tester | 60 | 20 | 7 | 8400
Hardware and Software Procurement |  |  |  | 50000
113800