## Choose_model
Scenario: You are assigned to develop a basic embedded system for an automotive industry application. The system will be a vehicle temperature monitoring system that reads the engine temperature using sensors and displays warnings on a small dashboard screen if the temperature exceeds a safe limit.
Choosed model: Waterfall model
Why to choose waterfall ?
Waterfall Model Feature | Description
Linear & Sequential Phases | The system can follow a clear path: requirements → design → implementation → testing → deployment.
Well-Defined Requirements | Requirements are stable: read engine temp, compare with threshold, show warning — no expected changes.
Emphasis on Documentation | Automotive systems need detailed documentation for compliance (e.g., ISO 26262).
Early Design Focus | Critical to get the hardware-software interface right from the start (sensors, display, MCU).
Dedicated Testing Phase | Enables thorough validation under controlled conditions — crucial for safety and reliability.
Easy to Manage | Ideal for small teams and straightforward systems like basic engine temperature monitoring.
No Overlapping Phases | Reduces confusion in safety-critical systems where process clarity is important.
Good for Low-Risk Projects | The project scope is simple and well understood, making Waterfall a low-risk, efficient choice.

## Project_break down
Break Down the Project into Tasks:
Task ID | Phase | Task Name | Description | Estimated Duration | Assigned To | Dependencies
ID01 | Requirement Analysis | Gather System Requirements | Collect requirements for sensors, display type, warning logic, temperature range, etc. | 5 days | Project Manager | None
ID02 |  | Feasibility Study | Analyze technical feasibility for embedded system in a vehicle environment. | 2 days | Embedded Systems Engineer | TaskID 01
ID03 | System Design | Hardware Design | Design circuit involving microcontroller, temperature sensor, and display. | 4 days | Embedded Systems Engineer | TaskID 02
ID04 |  | Software Design | Plan firmware architecture, flowcharts, and data handling logic. | 3 days | Software Developer | TaskID 02
ID05 | Implementation | Firmware Development | Write embedded C code to read sensor, evaluate temperature, and control display. | 10 days | Software Developer | TaskID 04
ID06 |  | Hardware Assembly & Wiring | Assemble sensor, microcontroller, power supply, and connect display hardware. | 4 days | Embedded Systems Engineer | TaskID 03
ID07 | Testing | Unit Testing | Test each module (sensor reading, display output, alerts) individually. | 3 days | QA/Test Engineer | Tasks ID 5, 6
ID08 |  | Integration Testing | Test combined system with sensor input triggering display alerts. | 4 days | QA/Test Engineer | Task ID O7
ID09 |  | System Testing | Perform end-to-end test under simulated vehicle conditions. | 3 days | QA/Test Engineer | Task ID 08
ID10 | Deployment | Install in Prototype Vehicle | Mount device, connect to power, test in real conditions. | 2 days | Embedded Systems Engineer | Task ID 09
ID11 |  | User Documentation & Training | Create user manual and basic training guide for system operation. | 2 days | Project Manager | TaskID 10
ID12 | Maintenance | Post-Deployment Support | Bug fixes and minor updates (as needed). | 3 days | Software Dev / Engineer | After Deployment
Total=45 Days

## Timeline
Timeline Estimation
Task ID | Task Name | Phase | Start Date | End Date | Duration (Days) | Week No. | Dependencies
1 | Gather System Requirements | Requirement Analysis | 2025-05-01 | 2025-05-05 | 5 | Week 1 | -
2 | Feasibility Study | Requirement Analysis | 2025-05-06 | 2025-05-07 | 2 | Week 1 | Task 1
3 | Hardware Design | System Design | 2025-05-08 | 2025-05-13 | 4 | Week 2 | Task 2
4 | Software Design | System Design | 2025-05-08 | 2025-05-12 | 3 | Week 2 | Task 2
5 | Firmware Development | Implementation | 2025-05-14 | 2025-05-27 | 10 | Weeks 3–4 | Task 4
6 | Hardware Assembly & Wiring | Implementation | 2025-05-14 | 2025-05-19 | 4 | Week 3 | Task 3
7 | Unit Testing | Testing | 2025-05-28 | 2025-05-30 | 3 | Week 5 | Tasks 5, 6
8 | Integration Testing | Testing | 2025-05-31 | 2025-06-04 | 4 | Week 5–6 | Task 7
9 | System Testing | Testing | 2025-06-05 | 2025-06-07 | 3 | Week 6 | Task 8
10 | Install in Prototype Vehicle | Deployment | 2025-06-08 | 2025-06-09 | 2 | Week 6 | Task 9
11 | Documentation & Training | Deployment | 2025-06-10 | 2025-06-11 | 2 | Week 6–7 | Task 10
12 | Post-Deployment Support | Maintenance | 2025-06-12 | Ongoing | Ongoing | Week 7+ | After Deployment
|  |  | 01-may-25 to 12-jun-25 |  | 42 Days | 7 Weeks

## cost&resources
Cost and Resources
Role | Responsibilities | Rate/hr (INR) | Hours/week | Weeks | Cost
Embedded Systems Engineer | Sensor integration, engine temperature reading, firmware development | 90 | 35 | 7 | 22050
Software Developer | Display logic, warning algorithms, basic UI on dashboard | 90 | 30 | 7 | 18900
UI/UX Designer | Design user interface for dashboard display, ensure usability and clarity. | 55 | 10 | 4 | 2200
QA/Test Engineer | Write test cases, validate temperature limits, perform HIL testing | 75 | 25 | 6 | 11250
Project Manager | Planning, coordinating Waterfall phases (Req → Design → Impl → Test → Deploy) | 100 | 10 | 7 | 7000
Hardware and software procurement | To realize and implement the temperature monitoring system |  |  |  | 30000
91400